## Plan
Project Implementation Plan
Task | Task | Delegated to | % complete
1 | WHSMS Report demonstrating WHS legislative compliance | Lianne | 100%
2 | WHSMS Report describing WHS legislative compliance | Lianne | 100%
3 | WHSMS Report evaluating WHS legislative compliance | Volunteer
4 | Style guide followed for BizOps | Paul | 0%
5 | Audit All 28 criteria items are met | Paul | 0% | ** Check the Criteria items tab for 'Volunteer' work.
6 | Induction plan template with example and explanatory information | Lianne | 100%
7 | Project implementation plan | Paul | 100%
8 | Project scope template | John and Nathan | 50%
9 | Risk management plan | Alex
10 | Sample project staff meeting agenda | George
11 | Sample WHS Hazard Identification form completed and cross referenced in report | Lianne
12 | WHS hazard report form template with example and explanatory information | Lianne | 100%
Additional documents - each to be accompanied with example and explanatory information
1 | Emergency contacts list | Lianne | 100%
2 | WHS hazard report from template | Lianne | 100%
3 | Induction plan template | Lianne | 100%
4 | WHS induction for contractors/visitors | Kieran | 0%
5 | Detailed WHS induction checklist for contractors | Lianne | 100%
6 | WHS training register with examples and explanatory information | Harry
7 | Risk management plan | Alex
8 | WHS hazard inspection procedure | Lianne | 100%
9 | WHS hazard inspection quick checklist | Volunteer
10 | Suggested asbestos register | Lianne | 100%
11 | Hazardous substances register | Lianne | 100%

## Criteria items
Task 5 - 28 Criteria Items
| Criteria | Delegate and Source | Refer to
1 | Describe how you critiqued ideas and information from WHS legislation, policies, procedures and programs | Paul | Project Implementation & adherence to the WHS Act Legislation
Ensure a Safe Workplace
Topic 1: 1A
(page 2)
2 | Explain how you identified duty holders and defined WHS responsibilities for all workplace personnel in the work area according to WHS legislation, policies, procedures and programs. | Lianne | WHSMS ch3.3 Responsibilities
Ensure a Safe Workplace
Topic 1: 1B
(page 19)
3 | Explain how you established, implemented, maintained and evaluated effective and compliant participation arrangements for managing WHS. | Lianne | WHSM ch3.4 Consultation and Communication Arrangements
Ensure a Safe Workplace
Topic 2: 2A
(page 34)
4 | Describe methods used to monitor adherence to legal and regulatory rights and responsibilities for self and others in relation to WHS. | Lianne | WHSM ch3.1 Work Health and Safety (WHS) Policy
WHSM ch3.6 WHS Risk Assessment
5 | Explain how you identified and approved financial and human resources required by the WHSMS. | Paul | Project Implementation
|  | John | & Project Scope
6 | Explain your strategies for working with contractors and their representatives to set up and maintain participation arrangements according to relevant WHS legislation. | Fanny | add to WHSM ch6 Report
Ensure a Safe Workplace
|  | Topic 2 | WHSM ch4.5
|  | (page 33) | Attachment 4 WHS Induction for Contractors/Visitors Attachment 5 Detailed WHS Induction Checklist for Contractors
Attachment 6 WHS Training Register
7 | Explain how you used consultative or collaborative processes as an integral part of the decision-making process. | Lianne | WHSM ch3.4 Consultation and Communication Arrangements
8 | What was your process for developing procedures for ongoing hazard identification, and assessment and control of associated risks? | Lianne | WHSM ch4.7 Workplace Hazard Inspections
Attachments 8
WHS Hazard Inspection Procedure
Attachment 9
WHS Hazard Inspection Quick Checklist
9 | Describe why it was essential that you included hazard identification at the planning stage. | Paul | Project Implementation
10 | How have you designed and evaluated stages of any change in the BizOps workplace to ensure that new hazards are not created by the proposed changes and existing hazards are controlled? | Volunteer | add to WHSM ch6 Report
|  | Ensure a Safe Workplace | Auditing process
Topic 3: 3B (page 67)
11 | How did you establish, implement, maintain and evaluate procedures for effectively identifying hazards? | Kelvin | add to WHSM ch6 Report
|  | Ensure a Safe Workplace | Auditing process
Topic 3
12 | Describe strategies deployed to assess and control BizOps risks using the hierarchy of risk control. | Alex | 7 Risk Management Plan Template
13 | How did you select and implement BizOps risk controls according to the hierarchy of control and WHS legislative requirements? | Alex | 7 Risk Management Plan Template
14 | Describe who in the BizOps workplace took responsibility for developing, implementing and reviewing policies, procedures and processes in accordance with organisational and legislative requirements. | Volunteer | add to WHSM ch6 Report
|  | Checklist Audit | reference:
WHSMS ch3.3 Responsibilities
Organisation Charts
Organisational Operational Plan
15 | Describe how you identified inadequacies in existing risk controls according to the hierarchy of control and WHS legislative requirements. | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 3: 3C & 3D
(page 71 & page 75)
16 | Explain the objective for promptly supplying resources to enable implementation of new measures. | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 3: 3D (page 78)
17 | What systematic analytical processes assisted you in gathering relevant BizOps information? | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 3
18 | Describe how you used identifying and evaluating options against agreed criteria. | Volunteer | add to WHSM ch6 Report
|  | Ensure a Safe Workplace | Audit
Topic 3: 3E
(page 80)
19 | Identify requirements for requesting expert WHS advice, and how you would request this advice. | Volunteer | add to WHSM ch6 Report
20 | Develop a suitable WHS induction and training program for all workers in a work area as part of the organisation's training program. | Kelvin | add to WHSM ch6 Report
Ensure a Safe Workplace
|  | Topic 4: 4A | WHSM ch4.5
|  | (page 90) | Attachment 3 Induction Plan Template
Attachment 6 WHS Training Register
21 | How did you establish, implement, maintain and evaluate effective and compliant participation arrangements for managing WHS, including identifying duty holders, identifying and approving the required resources, and developing and implementing a training program? | Paul | Project Implementation
Ensure a Safe Workplace
Topic 2
(page 33)
22 | Explain the system for WHS record keeping that you used and how you allowed for the identification of patterns of occupational injury and disease. | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 4: 4B
(page 95)
23 | Describe how you would record WHS decisions according to organisational requirements. | Nathaniel | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 4: 4B (page 99)
24 | How did you measure and evaluate the WHSMS in line with the organisation's quality systems framework? | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 4: 4C
(page 101) Check Pauls work
Refer to BizOps Company Business Plan Document
25 | Describe the methods used to establish, implement, maintain and evaluate a WHSMS for a work area of BizOps Enterprises in accordance with WHS legislation, including policies, procedures and record keeping. | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 3 & 4
26 | What improvements did you develop and implement into the WHSMS to achieve organisational WHS objectives? | Volunteer | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 4: 4D
(page 108)
27 | Describe the plans you developed or processes you used to manage relatively complex WHS management tasks with an awareness of how they may contribute to longer-term operational and strategic goals. | Volunteer | add to WHSM ch6 Report
After construction and implementation of the policies
28 | Explain how you ensured compliance with the WHS legislative framework to achieve, as a minimum, WHS legal requirements. | Josh | add to WHSM ch6 Report
Ensure a Safe Workplace
Topic 4: 4E
(page 112)
Checking legislation stated in document
And checking the website that it’s compliant
https://www.safeworkaustralia.gov.au/law-and-regulation